Orientation Activity

Responsibility Charting

Adapted from The Self-Renewing Congregation:  Strategies for Revitalizing Congregational Life by Isa Aron, pp117-118

Responsibility charting is a technique that helps working teams coordinate tasks and work together well.  Create a chart with as many rows as you have tasks plus a few extra.  List each task on a separate row.  Create a column for each person who will be involved in these tasks.  They can be involved in four different ways, as indicated by four letters:

R stands for the person (or people) responsible

A stands for the person (or people) who must approve

C stands for the person (or people) who must be consulted

I stands for the person (or people) who must be kept informed

# Step One

On the next page is an example of a responsibility chart for the preparation of bar and bat mitzvah students at one congregation.  Answer the following questions about this chart:

- What type of coordination is built into this structure?

- What additional coordination might be needed?

- What are the advantages/disadvantages of this arrangement?  What are the “weak links” in the chain, and how might we reinforce them?

# Step Two

On a following page is a list of potential Leadership Team responsibilities.

1.	Are there any additional tasks that you currently anticipate?

2.	Discuss these responsibilities and how you might want to divide them up among Leadership Team members and potentially people outside of the Leadership Team.

3.	Create a Responsibility Chart for these tasks.

# Sample Responsibility Chart for Bar/Bat Mitzvah Preparation

| Steps for Bar/Bat Mitzvah | Rabbi | Cantor | Educator | Teacher | Tutor |
| --- | --- | --- | --- | --- | --- |
| Learn Hebrew | C |  | A | R | I |
| Study of prayers | C | C | A | R | I |
| Meet with family 8 months before the bar/bat mitzvah | R |  |  |  |  |
| Create and update bar/bat mitzvah handbook | A | A | R |  |  |
| Coordinate correspondence regarding all meetings with tutor and rabbi |  | R |  |  |  |
| Individual tutoring 1x/week about the content of Torah portion and fluency decoding and chanting | I |  | A | I | R |
| Five session family workshop re:service | R | R | R |  |  |
| Three meetings with bar/bat mitzvah candidate regarding dvar torah | R |  |  |  |  |
| First rehearsal with family |  | R |  |  |  |
| Second rehearsal with family | R |  |  |  |  |

# Potential Leadership Team Tasks

## Planning meetings of the Leadership Teams

Prepare agenda for LT meeting (decide if it should include: connection, core discussions, text study, and reflections, like TF meetings do)

Call consultant to discuss issues and questions

## Planning Task Force meetings

Review the Guidebooks suggestions, and adapt them

Discuss plans for the meeting with the consultant

Lead the connection part of the meeting

Facilitate text study sessions

Facilitate core discussions

Lead reflections

## In between meeting tasks

Keep minutes of the meetings

Review and edit the minutes

Post minutes on the Team Workspace

Post contents of the vision folder on the Team Workspace

Check in with Task Force members who are absent

Send reminders about work to be done between meetings

Send notices of upcoming meetings

## Reflecting on the process:

Debrief the last TF meeting

Pay attention to how the TF is developing as a group: what issues (either content or process) are emerging that need to be addressed?

Discuss these issues with the consultant

Review this responsibility chart from time to time, to make adjustments

## Communications

Talk informally about the work of the Task Force to members of the congregation

Give reports on the work of the Task Force to the religious school committee

Give reports on the work of the Task Force to the board

Give reports on the work of the Task Force to parents

Give reports on the work of the Task Force to teachers

Give reports on the work of the Task Force to synagogue staff members

Write bulletin articles about the work of the Task Force